## Test Plan Blood Bank Today
BLOOD BANK TODAY
17 Attributes
Test Plan ID (Name) | Bloodbanktoday_1.1_MasterTestPlan_1.1
Introduction | A blood bank today is a center where blood gathered as a result of blood donation is stored and preserved for later use in blood transfusion.
Reference | Google, wiki
Test Item | 1. Registration 2. Log in. 3. Blood Bank Details. 4) Donor Details. 5) Patient Details. 6) Contact us. 7) About us |  | o`
Features to be tested | 1. Registration 2. Log in. 3. Blood Bank Details. 4) Donor Details. 5) Patient Details. 6) Contact us. 7) About us
Features not to be tested | WhatsApp icon
Test Environment | OS, Windows Browse: Microsoft Edge
Test Deliverables | 1) SRS 2) TEST PLAN 3) TEST CASES 4) DEFECT REPORTING 5) EXCEUTION LOG
Approach | Water Fall Model : The Application is having less modules. Black box Testing : Checking the functionality of the internal structure, code design
Suspend and Resume Criteria | 1) Suspend if while logging in system crashed. First and then resume 2) Suspend if donar details are not updated, update and then resume.
Entry and Exit Criteria | Test cases are failed and execute in some other area. 1) When all documents are baseline you start testing. 2) Exit if more than 90% test cases are ready
Risk and Contingencies | Risky if the employee is on leave. If software is not working or not. IF employees will left the job. If govt launched new project
Software Risk Issue | Risky if the employee is on leave. If software is not working or not.
Responsibilites | Roles | Responsibilites
| 1. Team Lead | Test Plan
| 2. Sr. Tester | Test Scenario
| 3.Sr. Tester | Test case
| 4.Jr.Tester | Defect Report
Schedule | Responsibility
1. Requirement gathering
2.Test Planning
3.Test Anaysis and Desginl
4. Test Implementation and Design
Staffing and Training Needs | 1) Hiring New Employees as per project need. 2) Training on the application/system.3) Training for any tools to be used
Approval | Name : Mrs Vishakha Desai
Test Planning and controlling | Test Planning by tes lead/test manager/project manager Prepared by test plan
Test Analysis And Design
Test Implementation and Execution
Evaluate Exit Criteria & Reporting
Test Closure Activities

## Test Plan Gmail
GMAIL
17 Attributes
Test Plan ID (Name) | Gmail_1.1_MasterTestPlan_1.1
Introduction | Gmail is a free email service provided by Google. As of 2019, it had 1.5 billion active users worldwide.[1] A user typically accesses Gmail in a web browser or the official mobile app. Google also supports the use of email clients via the POP and IMAP protocols.
Reference | BRS SRS Google Wikipidea
Test Item | 1. Login Page 2. Password Page 3. Inbox 4. Sent Mail 5.Forgot password 6.Draft mail 7. Important mail 8. Composed 9. Categories 10. Join Meeting 11.New meeting 12.Social Message 13. Promotion message 14.Favorite 15.Delete message 16. Search mail 17. My profile 18. Settings 19. Support
Features to be tested | 1. Login Page 2. Password Page 3. Inbox 4. Sent Mail 5.Forgot password 6.Draft mail 7. Important mail 8. Composed 9. Categories 10. Join Meeting 11.New meeting 12.Social Message 13. Promotion message 14.Favorite 15. My profile
Features not to be tested | 1. Search mail 2.Delete Message 3. Draft Mail 4. Snoozed 5. Settings 6. Support
Test Environment | OS: Windows, Android Database SQL Server 2000/2022 Laptop RAM Size: 8.00 GB, 64-bit operating system Browse : Microsoft Edge
Test Deliverables | 1) SRS 2) TEST PLAN 3) TEST CASES 4) DEFECT REPORTING 5) EXCEUTION LOG
Approach | Agile Model and Black box Testing
Suspend and Resume Criteria | 1) Suspend if while logging in system crashed. Fisit and then resume 2) Suspend if donar details are not updated, update and then resume.
Entry and Exit Criteria | Test cases are failed and execute in some other area. 1) When all documents are baseline you start testing. 2) Exit if more than 90% test cases are ready
Risk and Contingencies | Risky if the employee is on leave. If software is not working or not. IF employees will left the job. If govt launched new project
Software Risk Issue | Risky if the employee is on leave. If software is not working or not.
Responsibilites | Roles | Responsibilites
| 1. Team Lead | Test Plan
| 2. Sr. Tester | Test Scenario
| 3.Sr. Tester | Test case
| 4.Jr.Tester | Defect Report
Schedule | Responsibility
1. Requirement gathering
2.Test Planning
3.Test Anaysis and Desginl
4. Test Implementation and Design
Staffing and Training Needs | 1) Hiring New Employees as per project need. 2) Training on the application/system.3) Training for any tools to be used
Approval | Name : Mrs Vishakha Desai

## Use Case_Compose mail
Use Case : Compose Gmail
Use Case Id | Goal | Pre-Condition | Path | Actors | Step | Post-condition
Use Case_sending Messages A to B | To check functionality of goal | 1. Must have a Network connection | 1. Normal path : A to B send mail | Primary Actor : user | 1. Register Gmail account | Send Gmail
|  | 2. Must have a Internet connection | 2. Alternate path : A to B calling through others apps like whatsapp, line etc. |  | 2. Login Gmail
|  | 3. Gmail login page should working |  |  | 3. Compose Mail
4. Send Mail I,e attachments etc.

## Use_calling
Use Case : Calling A to B
Use Case Id | Goal | Pre-Condition | Path | Actors | Step | Post-condition
Use Case_calling A to B | To check functionality of goal | 1. Must have a Network connection | 1. Normal path : A to B calling | Primary Actor : user | 1. Unlock phone | connect the call.
|  | 2. Must have a Number | 2. Alternate path : A to B calling through others apps like whatsapp, line etc. |  | 2. open dial pad
|  | 3. Must have sim card | 3 |  | 3. To enter phone number.
|  | 4. Amount balance should be available |  |  | 4. press call button to call

## Test Scenario
Test Scenario ID | Test Scenario Name | Objective | Pre-Condition | Test Condition
TS_Registration_001 | Registration | To Check the functionality of registration page | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 1.1. To Check the functionality of registration page with Valid 1.2. To check the functionality of registration page with invalid 1.3. To check the functionality of registration page with all field blank. 1.4. To check the functionality of registration page only entering Mandatory field data. 1.5. To check the functionality of registration page with valid and invalid data 1.6. To check the functionality of registration page with only optional field
TS_Login_002 | Login | To Check the functionality of Login | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 2.1 to check functionality of login page functionality with valid username and valid document 2.2 to check functionality of login page functionality with invalid username and invalid password 2.3 to check functionality of login page functionality with invalid username and valid password 2.4 to check functionality of login page funcitionality with valid username and invalid password 2.5 to check functionality of login page functionality with empty username and empty password. 2.6 to check fuctionality of login page functionality with empty username and valid password 2.7 to check functionality of logn page functionality with valid username and empty password
TS_Findblood_003 | Find Blood | To check the functonality of Find Blood Group | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 3.1 to check functionality of find Blood Group button 3.2 to check functionality of select state 3.3 to check functionality of find Blood Group button 3.4 to check functionality of tesihil
TS_Requestblood_004 | Request Blood | to check functionality of To Request Blood Group | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 4.1 to check functionality of patient details i.e Patient name 4.2 to check the functionaliyt of patient detalis i.e Doctor Name 4.3 to check functionality of find Blood Group button 4.4 to check functionaliy of Select state 4.5 to check functionaliy of Select district 4.6 to check functionaliy of Select teshil 4.7 to check functionality of contact details 4.8 to check contact name 4.9 to check mobile no. date and when we need
TS_Blogs_005 | Blogs | to check the functionality of blog | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 5.0 to check whether it function navigating or not 5.1 To check all information
TS_Causes_006 | Causes | to check the functionality causes | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 6.0 to check functionality of donate now and more detail
TS_Event_007 | Events | to check the functionaliy of Events | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 7.0 to check the functionality of all information
TS_Donate us_008 | Donate us | to check the functionality of Donate us | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 8.0 to check the functionality of QR code whether it is work or not 8.1 to check the functionality of another way How much would you like to donate? 8.2 to check the functionality of amount button in box and enter amount 8.3 to check the functionality of donor details 8.4 to check the functionality of full name, email id, mobile no, country, state, city, pincode, address and display in the list Donate now
TS_Donate us_009 | News | to check the funcitonality of News | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 9.0 To check the functionality of News with facebook link 9.1 To check the funcitonality of news ith read more
TS_Dashboard_010 | Dashboard | to check the functionality of dashboard | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 10.1 To check functionality of Add blood donation report 10.2 To check functionality of copy link button 10.3 to check functionlality of donor register
TS_My message_011 | My Message | to check the functionality of My Message | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 11.1 To check functionality of Search message for 11.2 To check functionality of submit box
TS_Edit Profile_012 | Edit Profile | to check the functionality of Edit Profile | 1. Internet must be working 2. Browser must be working 3.URL must be working 4. Registration page must be working | 12.0 To check the functionality of persnal information edit option 12.1 To check the functionality of address box and contact informatiion 12.2 To check the functioonality of password
Register
login
Find Blood
Request Blood |  |  |  | tj
Blogs
Causes
Event
News
Video
More
Donate us
Dashboard
My message
Edit Profile

## Test Case
Test Case ID | Test Case Objective | precondition | step | step Description | Test Data | Expected Result | Actual Result | Status | Remark
TS_01_TC_01 | To Check the functionality of registration page with valid data | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Registration page must be working | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 | Enter Full Name Enter email Id Enter Mobile no: Create password Select Blood Group select gender select birth day select birth month select birth Year Enter weight Enter last donation day Enter last donation month Enter last donation year select Yes or no option for show mobile Select yes or no option for sms alert Enter pin/zip code select state Select district select teshil Enter city or village Accept Terms and conditions Enter submit button | Vinod kumar b.vinodkumar24@gmail.com 9731119371 123xyz B+ Male 24 October 1987 65 10 jun 2015 yes yes 560004 Karnataka Bangalore Bangalore Bangalore Clicked | 1. Entered name should be Accepted 2. Entered email should be Accepted 3. Entered mobile number should be Accepted 4. Entered password should be Accepted 5. Entered Blood Group should be Accepted 6. Entered Gender should be Accepted 7. Entered birth day should be Accepted 8. Entered birth month should be Accepted 9. Entered birth year should be displayed 10. Entered weight should be displayed 11. Entered last donation day should be displayed 12. Entered last donation month should be displayed 13. Entered last donation year should be displayed 14. Select option should be displayed 15. Select option should be displayed 16. Entered pin/zip code should be displayed 17. Selected state should be displayed 18. Selected district should be displayed 19. Selected tehsil should be displayed 20. Entered city or village should be displayed 21. Check box should be selected 22. Registration is done successfully and asking for entereing OTP | 1. Entered name should be Accepted 2. Entered email should be Accepted 3. Entered mobile number should be Accepted 4. Entered password should be Accepted 5. Entered Blood Group should be Accepted 6. Entered Gender should be Accepted 7. Entered birth day should be Accepted 8. Entered birth month should be Accepted 9. Entered birth year should be displayed 10. Entered weight should be displayed 11. Entered last donation day should be displayed 12. Entered last donation month should be displayed 13. Entered last donation year should be displayed 14. Select option should be displayed 15. Select option should be displayed 16. Entered pin/zip code should be displayed 17. Selected state should be displayed 18. Selected district should be displayed 19. Selected tehsil should be displayed 20. Entered city or village should be displayed 21. Check box should be selected 22. Registration is done successfully and asking for entereing OTP | Pass
TS_01_TC_02 | To Check the functionality of registration page with invalid data | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Registration page must be working | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 | Enter Full Name Enter email Id Enter Mobile no: Create password Select Blood Group select gender select birth day select birth month select birth Year Enter weight Enter last donation day Enter last donation month Enter last donation year select Yes or no option for show mobile Select yes or no option for sms alert Enter pin/zip code select state Select district select teshil Enter city or village Accept Terms and conditions Enter submit button | Vinod kumar46464 b.vinodkumar24@gmail.com 973111937148 123xyz B+e Male 24 October 1987 65 10 jun 2015 yes yes 5600ppp Karnataka bangalore bangalore bangalore clicked | 1. It should not accept full name 2. It should not accept gmail 3. It should not accept mobile number 4. It should accept password 5. It should accept blood group 6. It should accept gender 7. It should accept birth day 8. It should accept birth month 9. It should accept birth year 10. It should accept weight 11. It should accept last donation day 12. It should accept last donation month 13. It should accept last donation year 14. It should accept select yes or no option for show mobile 15. It should accept select yes or no option for sms alert 16. It should accept pincode 17. It should accept state 18. It should accept district 19. | 1. It should not accept full name 2. It should not accept gmail 3. It should not accept mobile number 4. It should accept password 5. It should accept blood group 6. It should accept gender 7. It should accept birth day 8. It should accept birth month 9. It should accept birth year 10. It should accept weight 11. It should accept last donation day 12. It should accept last donation month 13. It should accept last donation year 14. It should accept select yes or no option for show mobile 15. It should accept select yes or no option for sms alert 16. It should accept pincode 17. It should accept state 18. It should accept district 19. | Pass
TS_01_TC_03 | To check functionality of Register button with Blank | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Registration page must be working | 1 2 3 4 5 6 7 8 9 10 11 12 13 | Enter Full Name Enter email Id Enter Mobile no: Create password select Yes or no option for show mobile Select yes or no option for sms alert Enter pin/zip code select state Select district select teshil Enter city or village Accept Terms and conditions Enter submit button | blank blank blank 123xyz yes yes 560004 karnataka bangalore bangalore bangalore clicked | 1. It should be blank no acceped 2. It should blank gmail 3. It should blank number 4. It should blank password 5. It should blank last donation year 6. It should blank select yes or no option for show mobile 7. It should blank select yes or no option for sms alert 8. It should accept pincode 9. It should accept state 10. It should accept district | 1. It should be blank. 2. It should blank gmail 3. It should blank number 4. It should blank password 5. It should blank last donation year 6. It should blank select yes or no option for show mobile 7. It should blank select yes or no option for sms alert 8. It should accept pincode 9. It should accept state 10. It should accept district | Pass
TS_01_TC_04 | To check functionality of Registration page with only keeping mandatory field with valid and invalid data. | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Registration page must be working | 1 2 3 4 5 6 | Enter Full Name Select Blood Group select gender Enter weight select Yes or no option for show mobile Enter submit button | Vinod kumar B+ Male 65 yes clicked | 1. It should accept blood group 2. It should accept gender 3. It should accept weight 4. It should accept select yes or no option for show mobile 5.It should not accept submit button. | 1. It should accept blood group 2. It should accept gender 3. It should accept weight 4. It should accept select yes or no option for show mobile 5.It should not accept submit button. | Pass
`
TS_01_TC_05 | To check functionality of Registration page with valid and invalid | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Registration page must be working | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 | Enter Full Name Enter email Id Enter Mobile no: Create password Select Blood Group select gender select birth day select birth month select birth Year Enter weight Enter last donation day Enter last donation month Enter last donation year select Yes or no option for show mobile Select yes or no option for sms alert Enter pin/zip code select state Select district select teshil Enter city or village Accept Terms and conditions Enter submit button | Vinod kumar b.vinodkumar@gmail.com 9731119371aaa 123xyz B+e Male 24 October 1987 6p 10 jun 2015 yes yes 560004 karnataka bangalore bangalore bangalore clicked | 1. Entered name should not be Acceped 2. Entered email should be displayed 3. Entered mobile number should be displayed 4. Entered password should be displayed 5. Entered Blood Group should be displayed 6. Entered Gender should be displayed 7. Entered birth day should be displayed 8. Entered birth month should be displayed 9. Entered birth year should be displayed 10. Entered weight should be displayed 11. Entered last donation day should be displayed 12. Entered last donation month should be displayed 13. Entered last donation year should be displayed 14. Select option should be displayed 15. Select option should be displayed 16. Entered pin/zip code should be displayed 17. Selected state should be displayed 18. Selected district should be displayed 19. Selected tehsil should be displayed 20. Entered city or village should be displayed 21. Check box should be selected 22. Registration is done successfully and asking for entereing OTP | 1. Entered name should not be Acceped 2. Entered email should be displayed 3. Entered mobile number should be displayed 4. Entered password should be displayed 5. Entered Blood Group should be displayed 6. Entered Gender should be displayed 7. Entered birth day should be displayed 8. Entered birth month should be displayed 9. Entered birth year should be displayed 10. Entered weight should be displayed 11. Entered last donation day should be displayed 12. Entered last donation month should be displayed 13. Entered last donation year should be displayed 14. Select option should be displayed 15. Select option should be displayed 16. Entered pin/zip code should be displayed 17. Selected state should be displayed 18. Selected district should be displayed 19. Selected tehsil should be displayed 20. Entered city or village should be displayed 21. Check box should be selected 22. Registration is done successfully and asking for entereing OTP | Pass
TS_01_TC_06 | To check functionality of Registration page with only optional field | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Registration page must be working | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 | Enter email Id Enter Mobile no: Create password select birth day select birth month select birth Year Enter last donation day Enter last donation month Enter last donation year select Yes or no option for show mobile Enter pin/zip code select state Select district select teshil Enter city or village Accept Terms and conditions Enter submit button | b.vinodkumar24@gmail.com 9731119371 123xyz 24 October 1987 10 jun 2015 yes 560004 Karnataka Bangalore Bangalore Bangalore Clicked | 1. Entered email should be Accepted 2. Entered mobile number should be Accepted 3. Entered password should be Accepted 4.Entered birth day should be Accepted 5. Entered birth month should be Accepted 6. Entered birth year should be Accepted 7. Entered last donation day should be displayed 8. Entered last donation month should be displayed 9. Entered last donation year should be displayed 10. Select option should be displayed 11. Entered pin/zip code should be displayed 12. Selected state should be displayed 13. Selected district should be displayed 14. Selected tehsil should be displayed 15. Entered city or village should be displayed 16. Check box should be selected 17. Registration is not done successfully and asking for entereing OTP | 1. Entered email should be Accepted 2. Entered mobile number should be Accepted 3. Entered password should be Accepted 4.Entered birth day should be Accepted 5. Entered birth month should be Accepted 6. Entered birth year should be Accepted 7. Entered last donation day should be displayed 8. Entered last donation month should be displayed 9. Entered last donation year should be displayed 10. Select option should be displayed 11. Entered pin/zip code should be displayed 12. Selected state should be displayed 13. Selected district should be displayed 14. Selected tehsil should be displayed 15. Entered city or village should be displayed 16. Check box should be selected 17. Registration is done successfully and asking for entereing OTP | Pass
TS_02_TC_01 | To check functionality of login page functionality with valid username and valid Password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter Valid email Id or Mobile No Enter Valid Password Click in Sign In Button | Vino@gmail.com pass@xyz Clicked | 1. Entered Email should be Accepted 2. Entered password is accepted 3.Login should be successuly | 1. Entered Email should Accepted 2. Entered password accepted 3.Login should successuly | Pass
TS_02_TC_02 | To check functionality of login page functionality with Invalid username and Invalid password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter InValid email Id or Mobile No Enter InValid Password Click in Sign In Button | Vino@gmail.com pass@xyz Clicked | 1. Entered Email should not be Accepted 2. Entered password Should not be accepted 3.Login should not be successuly | 1. Entered Email should not Accepted 2. Entered password Should not accepted 3.Login should not successuly | Pass
TS_02_TC_03 | To check functionality of login page functionality with Blank username and Blank password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter Blank email Id or Mobile No Enter Blank Password Click in Sign In Button | Blank Blank Clicked | 1. Entered Blank Email should not be Accepted 2. Entered Blank password Should not be accepted 3.Login should not be successuly | 1. Entered Blank Email should not be Accepted 2. Entered Blank password Should not be accepted 3.Login should not be successuly | Pass
TS_02_TC_04 | To check functionality of login page functionality with Valid username and Blank password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter Valid email Id or Mobile No Enter Blank Password Click in Sign In Button | Vino@gmail.com Blank Clicked | 1. Entered valid Email id or mobile no should be Accepted 2. Entered Blank password Should not be accepted 3. Click on sign in button | 1. Entered valid Email id or mobile no should be Accepted 2. Entered Blank password Should not be accepted 3. Login is not sucessfully | Pass
TS_02_TC_05 | To check functionality of login page functionality with InValid username and Blank password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter Valid email Id or Mobile No Enter Blank Password Click in Sign In Button | Vino@gmail.com Blank Clicked | 1. Entered Invalid Email should not be Accepted 2. Entered Blank password Should not be accepted 3.Login should not be successuly | 1. Entered Blank Email should not be Accepted 2. Entered Blank password Should not be accepted 3.Login is not successuly | Pass
TS_02_TC_06 | To check functionality of login page functionality with InValid username and Blank password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter Blank email Id or Mobile No Enter Valid Password Click in Sign In Button | Blank Pass@123 Clicked | 1. Entered Blank Email id or mobile should not be Accepted 2. Entered valid password Should be accepted 3.Clicik on sign in button be sucessfully | 1. Entered Blank Email id or mobile is not Accepted 2. Entered Valid password is accepted 3.click on sign in button not be successuly | Pass
TS_02_TC_07 | To check functionality of login page functionality with IBlank username and Invalid password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter Blank email Id or Mobile No Enter InValid Password Click on Sign In Button | Blank Pa Clicked | 1. Entered Blank Email id or mobile should be Accepted 2. Entered Invalid password Should be accepted 3.Clicik on sign in button be sucessfully | 1. Entered Blank Email id or mobile is not Accepted 2. Entered InValid password is accepted 3.click on sign in button be successuly | Pass
TS_02_TC_08 | To check functionality of login page functionality with Invalid username and valid password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter Invalid email Id or Mobile No Enter Valid Password Click on Sign In Button | Vino@gmail.com Pass@123 Clicked | 1. Entered Invalid Email id or mobile should not be Accepted 2. Entered valid password Should not be accepted 3.Login should not be sucessfully | 1. Entered Invalid Email id is Accepted 2. Entered Valid password is accepted 3. Login should not be sucessfully | pass
TS_02_TC_09 | To check functionality of login page functionality with valid username and Invalid password | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Enter valid email Id or Mobile No Enter InValid Password Click on Sign In Button | Vino@gmail.com Pas Clicked | 1. Entered valid Email id or mobile should be Accepted 2. Enter invalid password Should not be accepted 3.Click on sign in button | 1. Entered valid Email id is Accepted 2. Entered inValid password not is accepted 3. click on sign in button is successful | pass
TS_02_TC_10 | To check functionality of login page with sign in with facebook | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 | Click on Signin With Facebook | clicked | Clicked on signin in with facebook should be sucessful | Clicked on signin in with facebook is not nav igating to respective links | Fail
TS_02_TC_11 | To check functionality of forgot password with valid email id | 1. Internet must be working 2. Browser must be working 3. URL must be working 4. Userr must be reigster user | 1 2 3 4 5 | Click on forgot password Enter Valid Email Id Click on send message Click on OTP Click on submit | Clicked Vino@gmail.com clicked Blank Clicked | 1. Click on Forgot Password link should be sucessful 2.Enter valid email should be accepted 3.Click on send message should be accepted 4. OTP should be received 5. Click on submit should be successful | 1. Click on Forgot Password link is sucessful 2.Enter valid email id is accepted 3.Click on send message is accepted 4. OTP is not received 5. Click on submit is not successful | Fail

## Defect Report
Defect ID | Defect Reporting date | Project Name | Module Name | Project Version | Types of defect | Phase in which defect is identifed | Summary of defect | Steps to produce | Expected result | Acutal Result | Test Data | Description of defect | severity | priority | status | Reported by | Reported to
D_01 | 14/01/2022 | Blood Bank Today | Registration | 1.1 | Wrong functional defect | System Testing | It wont allows us to do registration will all the mandatory filed and the send we recieve aeoo message I,e "Please fil out this field. | 1. Enter Full Name 2. Select Blood Group 3. select gender 4. Enter weight 5. select Yes or no option for show mobile 6. Enter submit button | 1. It should accept blood group 2. It should accept gender 3. It should accept weight 4. It should accept select yes or no option for show mobile 5.It should not accept submit button. | 1. It should accept blood group 2. It should accept gender 3. It should accept weight 4. It should accept select yes or no option for show mobile 5.It should not accept submit button. | Vinod kumar B+ Male 65 yes clicked | In Seen use can select blood group option, gender, Weight And submit button. | Low | High | New | Jr Tester
D_02 | 14/01/2022 | Blood Bank Today | Registration | 1.1 | Wrong functional defect | System Testing | It should not be acceped as | 1. Enter Full Name 2. Select Blood Group 3. select gender 4. Enter weight 5. select Yes or no option for show mobile 6. Enter submit button | 1. It should accept blood group 2. It should accept gender 3. It should accept weight 4. It should accept select yes or no option for show mobile 5.It should not accept submit button. | 1. It should accept blood group 2. It should accept gender 3. It should accept weight 4. It should accept select yes or no option for show mobile 5.It should not accept submit button. | Vinod kumar B+ Male 65 yes clicked | In Seen use can select blood group option, gender, Weight And submit button. | Low | High | New | Jr Tester
D_03 | 14/01/2022 | Blood Bank Today | Registration | 1.1 | Wrong functional defect | System Testing | we able to rerise with out mandatory field i.e opional fields | 1. Enter email Id 2. Enter Mobile no: 3. Create password 4. select birth day 5. select birth month 6. select birth Year 7. Enter last donation day 8. Enter last donation month 9. Enter last donation year 10. select Yes or no option for show mobile Enter pin/zip code 11select state Select district select teshil Enter city or village Accept Terms and conditions Enter submit button | 1. Entered email should be Accepted 2. Entered mobile number should be Accepted 3. Entered password should be Accepted 4.Entered birth day should be Accepted 5. Entered birth month should be Accepted 6. Entered birth year should be Accepted 7. Entered last donation day should be displayed 8. Entered last donation month should be displayed 9. Entered last donation year should be displayed 10. Select option should be displayed 11. Entered pin/zip code should be displayed 12. Selected state should be displayed 13. Selected district should be displayed 14. Selected tehsil should be displayed 15. Entered city or village should be displayed 16. Check box should be selected 17. Registration is not done successfully and asking for entereing OTP | 1. Entered email should be Accepted 2. Entered mobile number should be Accepted 3. Entered password should be Accepted 4.Entered birth day should be Accepted 5. Entered birth month should be Accepted 6. Entered birth year should be Accepted 7. Entered last donation day should be displayed 8. Entered last donation month should be displayed 9. Entered last donation year should be displayed 10. Select option should be displayed 11. Entered pin/zip code should be displayed 12. Selected state should be displayed 13. Selected district should be displayed 14. Selected tehsil should be displayed 15. Entered city or village should be displayed 16. Check box should be selected 17. Registration is done successfully and asking for entereing OTP | b.vinodkumar24@gmail.com 9731119371 123xyz 24 October 1987 10 jun 2015 yes 560004 Karnataka Bangalore Bangalore Bangalore Clicked | In Seen use can select blood group option, gender, Weight And submit button. | Low | High | New | Jr Tester
D_04 | 14/01/2022 | Blood Bank Today | Registration | 1.1
desai.vishaka1995@gmail.com